## Fixed
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Zendesk Client | Description | Ticket Number | Issue Link | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment
CRITICAL - P1 | Fixed | OPSfwaTechOps | rchambers | 13/Oct/25 16:19 | 11/Nov/25 09:41 | Internal Escalation | https://freewheel.zendesk.com/agent/tickets/258707 | All users external/ internal reporting receiving an error when logging into Appstream: Certificate-based authentication not available First report around 1:30 Central. Initially re-entering credentials would bypass this. Around 3pm Central users reported not being able to get in with the workaround. Chen reportedly working with AWS | ESC-86100 | https://jira.freewheel.tv/browse/ESC-86100 | 13/Oct/25 16:45;kgugerty;[~cphuah] is currently engaged with AWS AppStream Support actively troubleshooting the issue.;;; | 13/Oct/25 17:04;ahoskins;Workaround solution has been provided to customers while Chen continues to work with AWS on full resolution. At the current time only 10 users are being effected.;;; | 13/Oct/25 17:11;astefanov;Update from [~cphuah]: - Issue is on AWS side with certificate threshold we weren't aware was in place - Working with AWS personnel to increase threshold and resolve the issue Meanwhile: - Regular (non-SSO) users: they currently login using Active Directory (AD) password. The AWS issue results in a secondary login screen where they can retype their AD credentials and proceed. - SSO users: we'll need to generate a new AD password and send it to them so they can use the workaround above.;;; | 13/Oct/25 17:46;astefanov;[~cphuah] provided update: "_It is fixed now - Please test it. Thx!_" Multiple internal users are able to login with trainer and test accounts without the secondary prompt.;;; | 14/Oct/25 01:38;jmurphy;[~cphuah] [~astefanov] Please add more detail to what the "certificate threshold" is and pertains to.Â Also - was there a reason why this threshold was just exceeded or did something change that contributed to exceeding this?;;; | 14/Oct/25 11:39;astefanov;[~cphuah], could you provide more info on the root cause? Was the limit in number of certificates registered or IdPs integrated with; if so, did it stop working for all or just OneLogin; and why did it start happening in the afternoon but was OK in the morning? Or was it a limit in number authentication requests made; if so, what was different yesterday (a lighter day because of Columbus day and schools being off and some parents being off as well) than any other day?;;; | 14/Oct/25 12:47;kgugerty;[~astefanov] [~jmurphy]Â AWS has an account lifetime cap of 1 million certificate requests.Â This is for the entire 248790300697 [aws-strata-prd@freewheel.com¦mailto:aws-strata-prd@freewheel.com] account, not just the App Stream Service.Â When an account reaches that limit the certificates are denied which resulted in the error messages the clients were receiving.Â The cap can be raised upon request ( now set to 2 million, which should carry us for about 18 months).Â Â We were previously unaware of this cap.Â Â There is a case escalated with AWS for a query / report so we can monitor this threshold and receive notifications when we are again approaching the limit. cc [~cphuah]Â please correct if I misunderstood any of the above info.;;; | 17/Oct/25 11:41;astefanov;The following link was provided in a Teams meeting: https://docs.aws.amazon.com/acm/latest/userguide/acm-limits.html. It specifically lists (last row in table "The following general service quotas apply to your AWS account when using ACM"): Number of Private Certificates per CA (lifetime) 1,000,000;;; | 26/Oct/25 14:56;scriptrunner;This ticket has been pending for more than 5 days without updates. [~rchambers] please update it and reopen to ENG/OPS if you need further actions. Otherwise it will be automatically closed in 2 days.;;; | 28/Oct/25 18:02;astefanov;Per today's RCA call, the limit was actually increased to 5,000,000.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | tstrege | 18/Apr/25 10:39 | 12/Jun/25 10:12 | Internal Escalation | [https://freewheel.zendesk.com/agent/tickets/232770] | Menard Inc is reporting that they are getting "The database connection cannot be opened. Please contact your system administrator to verify the Database Connect String setting(s)." They are getting this when launching SBMS. I am able to replicate in the trainer account.Their SQL server is SQLMBAGSBMSPR23\I17 Both Anson (4806) SQLMBAGSBMSPR23\I13 and The St. Gregory Group (3389) SQLMBAGSBMSPR23\I14 have reported the same problem now. Samer server SQLMBAGSBMSPR23 !image-2025-04-18-08-48-11-767.png! | ESC-78935 | https://jira.freewheel.tv/browse/ESC-78935 | 18/Apr/25 10:42;sthalapally;An OPS ticket exists for this ticket. Assigning ticket to TechOps.;;; | 18/Apr/25 10:51;jmurphy;DBA and Strata Tech Ops teams are engaged;;; | 18/Apr/25 10:54;tstrege;[~vfava] [~kyasa] Both Anson (4806) and The St. Gregory Group 3389 have reported the same problem now. Samer server SQLMBAGSBMSPR23;;; | 18/Apr/25 14:41;tstrege;Keith GugertyKeith GugertyÂ Â [1:35 PM¦https://freewheel.slack.com/archives/C08NWKW9QRJ/p1745001319621969] Root cause - Windows Updates for SQL Servers fails on automated install.Â When this fails the logs produced are about 700MB in size.Â This was paused after the last round of windows updates, but the pause expired and the updates resumed. there is a current open case with Microsoft to investigate this failure. Nagios Drive alerting for the system drive has automation in place to catch it at 10 GB, then kick off automation to clean up temp files to clear the alert.SQL Server specific monitoring has been setup to alert instead of kick off the automation.Separate automation has been setup to clear out older log files in the directory where they accumulate.;;; | 18/Apr/25 14:42;tstrege;Keith GugertyÂ Â [1:35 PM¦https://freewheel.slack.com/archives/C08NWKW9QRJ/p1745001319621969] Root cause - Windows Updates for SQL Servers fails on automated install.Â When this fails the logs produced are about 700MB in size.Â This was paused after the last round of windows updates, but the pause expired and the updates resumed. there is a current open case with Microsoft to investigate this failure. Nagios Drive alerting for the system drive has automation in place to catch it at 10 GB, then kick off automation to clean up temp files to clear the alert.SQL Server specific monitoring has been setup to alert instead of kick off the automation.Separate automation has been setup to clear out older log files in the directory where they accumulate.;;; | 18/Apr/25 14:48;jmurphy;From [~tstrege] First client report was at 8:21am. Zendesk ticket escalated to CS3 at 8:33am;;; | 18/Apr/25 14:48;jmurphy;Resolved as of 11:07a CT;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | flarose | 16/Dec/25 12:07 | 03/Feb/26 11:48 | Internal Escalation |  | Can you create a new alias to shared mailbox +data.setup@freewheel.com+ for DAN FR (Dentsu France) META integration : *dan.fr.meta@freewheel.com* Thanks | ESC-89061 | https://jira.freewheel.tv/browse/ESC-89061 | 03/Feb/26 11:48;jmurphy;The specified changes have been made to this shared mailbox on 12/4/2025. The address dan.fr.ias@freewheel.com is setup as a secondary alias. Please allow up to 24-48 hours for these changes to propagate.;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | jpham | 25/Mar/25 14:24 | 26/Mar/25 10:45 | Internal Escalation | https://freewheel.zendesk.com/agent/#/tickets/228605 | TO REQUESTOR: A user at Walz Tetrick Advertising is looking for a backup copy of her campaign in VIEW from yesterday, 3/24/2025, after 12 PM. The user located a backup file from 12 PM, but would like a newer copy of this file from the same day, if possible. Network ID: 1763 Summary of the issue report (symptom): Provided and collected diagnostic information: MRM/RPM URL: Live Page/App URL: Initial investigation results: Required actions from Engineers (if any): Please check and restore the campaign file named '25 HRB 2Q Gainsville.cp0' that was saved under S:\STRATA\VIEW32\USERS\KPETERSON5\HARD ROCK BET\2025 from yesterday, 3/24/2025, after 12 PM. Let me know if you have any questions. | ESC-77770 | https://jira.freewheel.tv/browse/ESC-77770 | 25/Mar/25 15:39;RShimelfarb;[~jpham] , is there a problem with opening the '{*}25 HRB 2Q Gainsville.cp0{*}' file that was saved under S:\STRATA\VIEW32\USERS\KPETERSON5\HARD ROCK BET\2025 from yesterday, 3/24/2025, after 12 PM? If so, please attach this file to the ticket so that engineers can troubleshoot. Thank you.;;; | 25/Mar/25 16:17;jpham;[~RShimelfarb] I think this may have been assigned to the wrong team. The issue isn't with the program or the campaign file. The buyer is looking to restore a backup file of this campaign from yesterday. I am going to close this ticket so I can create a new one in Jira directly to go to the correct group. Sorry for any inconvenience, and thank you for looking and responding.;;; | 25/Mar/25 16:20;jpham;I apologize, [~RShimelfarb], but it looks like I am unable to close this ticket since it is not an option for me.Â Can you please close it for me? I've cloned the case and created a new one to go to the correct group. Please let me know if you have any questions and thanks again for your help!;;; | 25/Mar/25 17:46;astefanov;Closed based on the comments, but since there is OPS ticket attached to this ESC and the OPS ticket isn't done yet, I'll reopen the ESC ticket so it can track the OPS status.;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 21/May/25 14:35 | 22/May/25 20:28 | Internal Escalation | https://freewheel.zendesk.com/agent/#/tickets/237574 | Gary Zerella is placing a request to have the agency's SBMS upgraded to version 25.1 in their production environment (Icon International, Inc Prod - 1789) along with Group 2 on 5/31/2025. Icon is in upgrade Group 5 but Gary would like to have the upgrade scheduled along with upgrade Group 2. The agency's server is SQLV6\I1 and domain is 1789B.gotostrata.com. Can we schedule this upgrade for Icon on this date? | ESC-80322 | https://jira.freewheel.tv/browse/ESC-80322 | 22/May/25 20:27;cphuah;Scheduled on 5/31/25 - OPS-227167;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 29/Apr/25 13:27 | 15/May/25 21:46 | Internal Escalation | https://freewheel.zendesk.com/agent/#/tickets/233623 | Horizon Media (860) needs help pinpointing performance issues that seem to be local to Brandon Clark and his team. Franklin would like to know if we can monitor and provide reports on the Horizon SQL server for several days? Ideally, we'd like to see performance for Brandon Clark or his session ID from 4/24-5/7. If we cannot filter to a specific personal, all user data works as well. Are you able to provide me the reporting every 24/48 hours? | ESC-79408 | https://jira.freewheel.tv/browse/ESC-79408 | 29/Apr/25 14:04;cphuah;The SQL trace and DPA have been setup by the DBA, and and we will be monitoring it this week.;;; | 29/Apr/25 18:35;ssalas;[~cphuah] Gerald Foston noted that Martha Carpio under username mcarpio has been stuck clearing invoices in SBMS since today 4/29/2025 at 4:30PM CST. I see that the agency's DB is being monitored. Please note this occurrence. Thanks.;;; | 30/Apr/25 15:25;cphuah;+ [~vfava] and [~kyasa] will look into the sql log.;;; | 07/May/25 15:10;ssalas;/[~vfava] [~kyasa] Gerald Foston noted slowness occurring today Wednesday 5/7/2025 at 12PM EST. Gerald suspects that the clearing of invoices in SBMS might have been the cause of the slowness. He states that the possible users that were clearing invoices at the time would be either Martha Carpio (under username mcarpio) and Annette Johnson (under username annjohnson) Could you look into the sql log around this time from today? cc: [~cphuah]Â ;;; | 08/May/25 11:18;ssalas;[~vfava] [~kyasa] Gerald Foston is reporting another occurrence of unexpected behavior from yesterday Wednesday 5/7/2025 at around 8:40PM EST. Jose Rosa (under username jrosa) was clearing invoices in the Invoice Status screen for client name "Carvana" for the broadcast month of February 2025 (1/27/2025 - 2/23/2025) in the Spot module. Jose received error "Invalid operation. The connection is closed." !Invoice Status error 1.jpg! Clicking the "Continue" button produced error "Error in Procedure Form_InvoiceStatus.VerifyRefreshSelectedClearedStatusChange()." !Invoice Status error 2.jpg! Moreover, Gerald Foston noted that Naliah Mohammed (under username nmohammed) was also having issues saving draft in the Media Billing module through the Client Billing screen.Â cc: [~cphuah]Â ;;; | 15/May/25 21:46;astefanov;Request was added to OPS-224886 to confirm database maintenance executes successfully, and additionally to fully reindex the database on the weekend (based on the time that takes, some additional coordination with Product and the client may be needed). Separately, per Chen, there is an active discussion to archive data from the HMI database - currently at 20+ years - and leave only last 7 years. This will require additional work and testing, so it's not a confirmed decision yet. Either one of those should address performance issues. Closing this ticket. Future performance issues may result in new ESC tickets and we'll follow up on the progress on OPS-224886.;;;