## Fixed
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Problem | Solution
CRITICAL - P1 | Fixed | OPSfwaTechOps | rchambers | 13/Oct/25 16:19 | 11/Nov/25 09:41 | Internal Escalation | ALL | Strata | T3 | MRM Only | https://freewheel.zendesk.com/agent/tickets/258707 | All users external/ internal reporting receiving an error when logging into Appstream: Certificate-based authentication not available First report around 1:30 Central. Initially re-entering credentials would bypass this. Around 3pm Central users reported not being able to get in with the workaround. Chen reportedly working with AWS | ESC-86100 | https://jira.freewheel.tv/browse/ESC-86100 | All users external/ internal reporting receiving an error when logging into Appstream: Certificate-based authentication not available First report around 1:30 Central. Initially re-entering credentials would bypass this. Around 3pm Central users reported not being able to get in with the workaround.
MAJOR - P2 | Fixed | OPSfwaTechOps | tstrege | 18/Apr/25 10:39 | 12/Jun/25 10:12 | Internal Escalation | Strata Client |  |  | MRM Only | [https://freewheel.zendesk.com/agent/tickets/232770] | Menard Inc is reporting that they are getting "The database connection cannot be opened. Please contact your system administrator to verify the Database Connect String setting(s)." They are getting this when launching SBMS. I am able to replicate in the trainer account.Their SQL server is SQLMBAGSBMSPR23\I17 Both Anson (4806) SQLMBAGSBMSPR23\I13 and The St. Gregory Group (3389) SQLMBAGSBMSPR23\I14 have reported the same problem now. Samer server SQLMBAGSBMSPR23 !image-2025-04-18-08-48-11-767.png! | ESC-78935 | https://jira.freewheel.tv/browse/ESC-78935 | Menard Inc is reporting that they are getting "The database connection cannot be opened. Please contact your system administrator to verify the Database Connect String setting(s)." They are getting this when launching SBMS. I am able to replicate in the trainer account.Their SQL server is SQLMBAG
NORMAL - P3 | Fixed | OPSfwaTechOps | flarose | 16/Dec/25 12:07 | 03/Feb/26 11:48 | Internal Escalation | ALL | Strata | T3 | MRM Only |  | Can you create a new alias to shared mailbox +data.setup@freewheel.com+ for DAN FR (Dentsu France) META integration : *dan.fr.meta@freewheel.com* Thanks | ESC-89061 | https://jira.freewheel.tv/browse/ESC-89061 | Can you create a new alias to shared mailbox +data.setup@freewheel.com+ for DAN FR (Dentsu France) META integration : *dan.fr.meta@freewheel.com* Thanks
NORMAL - P3 | Fixed | OPSfwaTechOps | jpham | 25/Mar/25 14:24 | 26/Mar/25 10:45 | Internal Escalation | Strata Client |  |  | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/228605 | TO REQUESTOR: A user at Walz Tetrick Advertising is looking for a backup copy of her campaign in VIEW from yesterday, 3/24/2025, after 12 PM. The user located a backup file from 12 PM, but would like a newer copy of this file from the same day, if possible. Network ID: 1763 Summary of the issue report (symptom): Provided and collected diagnostic information: MRM/RPM URL: Live Page/App URL: Initial investigation results: Required actions from Engineers (if any): Please check and restore the campaign file named '25 HRB 2Q Gainsville.cp0' that was saved under S:\STRATA\VIEW32\USERS\KPETERSON5\HARD ROCK BET\2025 from yesterday, 3/24/2025, after 12 PM. Let me know if you have any questions. | ESC-77770 | https://jira.freewheel.tv/browse/ESC-77770 | TO REQUESTOR: A user at Walz Tetrick Advertising is looking for a backup copy of her campaign in VIEW from yesterday, 3/24/2025, after 12 PM. The user located a backup file from 12 PM, but would like a newer copy of this file from the same day, if possible. Network ID: 1763 Summary of the issue repo
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 21/May/25 14:35 | 22/May/25 20:28 | Internal Escalation | Strata Client | Strata |  | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/237574 | Gary Zerella is placing a request to have the agency's SBMS upgraded to version 25.1 in their production environment (Icon International, Inc Prod - 1789) along with Group 2 on 5/31/2025. Icon is in upgrade Group 5 but Gary would like to have the upgrade scheduled along with upgrade Group 2. The agency's server is SQLV6\I1 and domain is 1789B.gotostrata.com. Can we schedule this upgrade for Icon on this date? | ESC-80322 | https://jira.freewheel.tv/browse/ESC-80322 | Gary Zerella is placing a request to have the agency's SBMS upgraded to version 25.1 in their production environment (Icon International, Inc Prod - 1789) along with Group 2 on 5/31/2025. Icon is in upgrade Group 5 but Gary would like to have the upgrade scheduled along with upgrade Group 2. The age
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 29/Apr/25 13:27 | 15/May/25 21:46 | Internal Escalation | Strata Client |  | T3 | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/233623 | Horizon Media (860) needs help pinpointing performance issues that seem to be local to Brandon Clark and his team. Franklin would like to know if we can monitor and provide reports on the Horizon SQL server for several days? Ideally, we'd like to see performance for Brandon Clark or his session ID from 4/24-5/7. If we cannot filter to a specific personal, all user data works as well. Are you able to provide me the reporting every 24/48 hours? | ESC-79408 | https://jira.freewheel.tv/browse/ESC-79408 | Horizon Media (860) needs help pinpointing performance issues that seem to be local to Brandon Clark and his team. Franklin would like to know if we can monitor and provide reports on the Horizon SQL server for several days? Ideally, we'd like to see performance for Brandon Clark or his session ID f