## 2025
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Client Support Type | Latest Status Summary | Zendesk Client | Description | Ticket Number | FIXED VERSION | Issue Link | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment
CRITICAL - P1 | Fixed | OPSfwaTechOps | rchambers | 13/Oct/25 16:19 | 11/Nov/25 09:41 | Internal Escalation | ALL | Strata | T3 | MRM Only |  | https://freewheel.zendesk.com/agent/tickets/258707 | All users external/ internal reporting receiving an error when logging into Appstream: Certificate-based authentication not available First report around 1:30 Central. Initially re-entering credentials would bypass this. Around 3pm Central users reported not being able to get in with the workaround. Chen reportedly working with AWS | ESC-86100 |  | https://jira.freewheel.tv/browse/ESC-86100 | 13/Oct/25 16:45;kgugerty;[~cphuah] is currently engaged with AWS AppStream Support actively troubleshooting the issue.;;; | 13/Oct/25 17:04;ahoskins;Workaround solution has been provided to customers while Chen continues to work with AWS on full resolution. At the current time only 10 users are being effected.;;; | 13/Oct/25 17:11;astefanov;Update from [~cphuah]: - Issue is on AWS side with certificate threshold we weren't aware was in place - Working with AWS personnel to increase threshold and resolve the issue Meanwhile: - Regular (non-SSO) users: they currently login using Active Directory (AD) password. The AWS issue results in a secondary login screen where they can retype their AD credentials and proceed. - SSO users: we'll need to generate a new AD password and send it to them so they can use the workaround above.;;; | 13/Oct/25 17:46;astefanov;[~cphuah] provided update: "_It is fixed now - Please test it. Thx!_" Multiple internal users are able to login with trainer and test accounts without the secondary prompt.;;; | 14/Oct/25 01:38;jmurphy;[~cphuah] [~astefanov] Please add more detail to what the "certificate threshold" is and pertains to.Â Also - was there a reason why this threshold was just exceeded or did something change that contributed to exceeding this?;;; | 14/Oct/25 11:39;astefanov;[~cphuah], could you provide more info on the root cause? Was the limit in number of certificates registered or IdPs integrated with; if so, did it stop working for all or just OneLogin; and why did it start happening in the afternoon but was OK in the morning? Or was it a limit in number authentication requests made; if so, what was different yesterday (a lighter day because of Columbus day and schools being off and some parents being off as well) than any other day?;;; | 14/Oct/25 12:47;kgugerty;[~astefanov] [~jmurphy]Â AWS has an account lifetime cap of 1 million certificate requests.Â This is for the entire 248790300697 [aws-strata-prd@freewheel.com¦mailto:aws-strata-prd@freewheel.com] account, not just the App Stream Service.Â When an account reaches that limit the certificates are denied which resulted in the error messages the clients were receiving.Â The cap can be raised upon request ( now set to 2 million, which should carry us for about 18 months).Â Â We were previously unaware of this cap.Â Â There is a case escalated with AWS for a query / report so we can monitor this threshold and receive notifications when we are again approaching the limit. cc [~cphuah]Â please correct if I misunderstood any of the above info.;;; | 17/Oct/25 11:41;astefanov;The following link was provided in a Teams meeting: https://docs.aws.amazon.com/acm/latest/userguide/acm-limits.html. It specifically lists (last row in table "The following general service quotas apply to your AWS account when using ACM"): Number of Private Certificates per CA (lifetime) 1,000,000;;; | 26/Oct/25 14:56;scriptrunner;This ticket has been pending for more than 5 days without updates. [~rchambers] please update it and reopen to ENG/OPS if you need further actions. Otherwise it will be automatically closed in 2 days.;;; | 28/Oct/25 18:02;astefanov;Per today's RCA call, the limit was actually increased to 5,000,000.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | tstrege | 18/Apr/25 10:39 | 12/Jun/25 10:12 | Internal Escalation | Strata Client |  |  | MRM Only |  | [https://freewheel.zendesk.com/agent/tickets/232770] | Menard Inc is reporting that they are getting "The database connection cannot be opened. Please contact your system administrator to verify the Database Connect String setting(s)." They are getting this when launching SBMS. I am able to replicate in the trainer account.Their SQL server is SQLMBAGSBMSPR23\I17 Both Anson (4806) SQLMBAGSBMSPR23\I13 and The St. Gregory Group (3389) SQLMBAGSBMSPR23\I14 have reported the same problem now. Samer server SQLMBAGSBMSPR23 !image-2025-04-18-08-48-11-767.png! | ESC-78935 |  | https://jira.freewheel.tv/browse/ESC-78935 | 18/Apr/25 10:42;sthalapally;An OPS ticket exists for this ticket. Assigning ticket to TechOps.;;; | 18/Apr/25 10:51;jmurphy;DBA and Strata Tech Ops teams are engaged;;; | 18/Apr/25 10:54;tstrege;[~vfava] [~kyasa] Both Anson (4806) and The St. Gregory Group 3389 have reported the same problem now. Samer server SQLMBAGSBMSPR23;;; | 18/Apr/25 14:41;tstrege;Keith GugertyKeith GugertyÂ Â [1:35 PM¦https://freewheel.slack.com/archives/C08NWKW9QRJ/p1745001319621969] Root cause - Windows Updates for SQL Servers fails on automated install.Â When this fails the logs produced are about 700MB in size.Â This was paused after the last round of windows updates, but the pause expired and the updates resumed. there is a current open case with Microsoft to investigate this failure. Nagios Drive alerting for the system drive has automation in place to catch it at 10 GB, then kick off automation to clean up temp files to clear the alert.SQL Server specific monitoring has been setup to alert instead of kick off the automation.Separate automation has been setup to clear out older log files in the directory where they accumulate.;;; | 18/Apr/25 14:42;tstrege;Keith GugertyÂ Â [1:35 PM¦https://freewheel.slack.com/archives/C08NWKW9QRJ/p1745001319621969] Root cause - Windows Updates for SQL Servers fails on automated install.Â When this fails the logs produced are about 700MB in size.Â This was paused after the last round of windows updates, but the pause expired and the updates resumed. there is a current open case with Microsoft to investigate this failure. Nagios Drive alerting for the system drive has automation in place to catch it at 10 GB, then kick off automation to clean up temp files to clear the alert.SQL Server specific monitoring has been setup to alert instead of kick off the automation.Separate automation has been setup to clear out older log files in the directory where they accumulate.;;; | 18/Apr/25 14:48;jmurphy;From [~tstrege] First client report was at 8:21am. Zendesk ticket escalated to CS3 at 8:33am;;; | 18/Apr/25 14:48;jmurphy;Resolved as of 11:07a CT;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | flarose | 16/Dec/25 12:07 | 03/Feb/26 11:48 | Internal Escalation | ALL | Strata | T3 | MRM Only |  |  | Can you create a new alias to shared mailbox +data.setup@freewheel.com+ for DAN FR (Dentsu France) META integration : *dan.fr.meta@freewheel.com* Thanks | ESC-89061 |  | https://jira.freewheel.tv/browse/ESC-89061 | 03/Feb/26 11:48;jmurphy;The specified changes have been made to this shared mailbox on 12/4/2025. The address dan.fr.ias@freewheel.com is setup as a secondary alias. Please allow up to 24-48 hours for these changes to propagate.;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | jpham | 25/Mar/25 14:24 | 26/Mar/25 10:45 | Internal Escalation | Strata Client |  |  | MRM Only |  | https://freewheel.zendesk.com/agent/#/tickets/228605 | TO REQUESTOR: A user at Walz Tetrick Advertising is looking for a backup copy of her campaign in VIEW from yesterday, 3/24/2025, after 12 PM. The user located a backup file from 12 PM, but would like a newer copy of this file from the same day, if possible. Network ID: 1763 Summary of the issue report (symptom): Provided and collected diagnostic information: MRM/RPM URL: Live Page/App URL: Initial investigation results: Required actions from Engineers (if any): Please check and restore the campaign file named '25 HRB 2Q Gainsville.cp0' that was saved under S:\STRATA\VIEW32\USERS\KPETERSON5\HARD ROCK BET\2025 from yesterday, 3/24/2025, after 12 PM. Let me know if you have any questions. | ESC-77770 |  | https://jira.freewheel.tv/browse/ESC-77770 | 25/Mar/25 15:39;RShimelfarb;[~jpham] , is there a problem with opening the '{*}25 HRB 2Q Gainsville.cp0{*}' file that was saved under S:\STRATA\VIEW32\USERS\KPETERSON5\HARD ROCK BET\2025 from yesterday, 3/24/2025, after 12 PM? If so, please attach this file to the ticket so that engineers can troubleshoot. Thank you.;;; | 25/Mar/25 16:17;jpham;[~RShimelfarb] I think this may have been assigned to the wrong team. The issue isn't with the program or the campaign file. The buyer is looking to restore a backup file of this campaign from yesterday. I am going to close this ticket so I can create a new one in Jira directly to go to the correct group. Sorry for any inconvenience, and thank you for looking and responding.;;; | 25/Mar/25 16:20;jpham;I apologize, [~RShimelfarb], but it looks like I am unable to close this ticket since it is not an option for me.Â Can you please close it for me? I've cloned the case and created a new one to go to the correct group. Please let me know if you have any questions and thanks again for your help!;;; | 25/Mar/25 17:46;astefanov;Closed based on the comments, but since there is OPS ticket attached to this ESC and the OPS ticket isn't done yet, I'll reopen the ESC ticket so it can track the OPS status.;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 21/May/25 14:35 | 22/May/25 20:28 | Internal Escalation | Strata Client | Strata |  | MRM Only |  | https://freewheel.zendesk.com/agent/#/tickets/237574 | Gary Zerella is placing a request to have the agency's SBMS upgraded to version 25.1 in their production environment (Icon International, Inc Prod - 1789) along with Group 2 on 5/31/2025. Icon is in upgrade Group 5 but Gary would like to have the upgrade scheduled along with upgrade Group 2. The agency's server is SQLV6\I1 and domain is 1789B.gotostrata.com. Can we schedule this upgrade for Icon on this date? | ESC-80322 |  | https://jira.freewheel.tv/browse/ESC-80322 | 22/May/25 20:27;cphuah;Scheduled on 5/31/25 - OPS-227167;;;
NORMAL - P3 | Fixed | OPSfwaTechOps | ssalas | 29/Apr/25 13:27 | 15/May/25 21:46 | Internal Escalation | Strata Client |  | T3 | MRM Only |  | https://freewheel.zendesk.com/agent/#/tickets/233623 | Horizon Media (860) needs help pinpointing performance issues that seem to be local to Brandon Clark and his team. Franklin would like to know if we can monitor and provide reports on the Horizon SQL server for several days? Ideally, we'd like to see performance for Brandon Clark or his session ID from 4/24-5/7. If we cannot filter to a specific personal, all user data works as well. Are you able to provide me the reporting every 24/48 hours? | ESC-79408 |  | https://jira.freewheel.tv/browse/ESC-79408 | 29/Apr/25 14:04;cphuah;The SQL trace and DPA have been setup by the DBA, and and we will be monitoring it this week.;;; | 29/Apr/25 18:35;ssalas;[~cphuah] Gerald Foston noted that Martha Carpio under username mcarpio has been stuck clearing invoices in SBMS since today 4/29/2025 at 4:30PM CST. I see that the agency's DB is being monitored. Please note this occurrence. Thanks.;;; | 30/Apr/25 15:25;cphuah;+ [~vfava] and [~kyasa] will look into the sql log.;;; | 07/May/25 15:10;ssalas;/[~vfava] [~kyasa] Gerald Foston noted slowness occurring today Wednesday 5/7/2025 at 12PM EST. Gerald suspects that the clearing of invoices in SBMS might have been the cause of the slowness. He states that the possible users that were clearing invoices at the time would be either Martha Carpio (under username mcarpio) and Annette Johnson (under username annjohnson) Could you look into the sql log around this time from today? cc: [~cphuah]Â ;;; | 08/May/25 11:18;ssalas;[~vfava] [~kyasa] Gerald Foston is reporting another occurrence of unexpected behavior from yesterday Wednesday 5/7/2025 at around 8:40PM EST. Jose Rosa (under username jrosa) was clearing invoices in the Invoice Status screen for client name "Carvana" for the broadcast month of February 2025 (1/27/2025 - 2/23/2025) in the Spot module. Jose received error "Invalid operation. The connection is closed." !Invoice Status error 1.jpg! Clicking the "Continue" button produced error "Error in Procedure Form_InvoiceStatus.VerifyRefreshSelectedClearedStatusChange()." !Invoice Status error 2.jpg! Moreover, Gerald Foston noted that Naliah Mohammed (under username nmohammed) was also having issues saving draft in the Media Billing module through the Client Billing screen.Â cc: [~cphuah]Â ;;; | 15/May/25 21:46;astefanov;Request was added to OPS-224886 to confirm database maintenance executes successfully, and additionally to fully reindex the database on the weekend (based on the time that takes, some additional coordination with Product and the client may be needed). Separately, per Chen, there is an active discussion to archive data from the HMI database - currently at 20+ years - and leave only last 7 years. This will require additional work and testing, so it's not a confirmed decision yet. Either one of those should address performance issues. Closing this ticket. Future performance issues may result in new ESC tickets and we'll follow up on the progress on OPS-224886.;;;

## 2024
FIXED
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Latest Status Summary | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Comments | Fix Version
CRITICAL - P1 | Fixed | OPSfwaTechOps | hschmeckpeper | 9/10/2024 11:47 | 9/13/2024 11:02 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | 40+ agencies not able to access buy.gotostrata.com | ESC-70893 | https://jira.freewheel.tv/browse/ESC-70893 | 10/Sep/24 12:07;kgugerty;Currently investigating connection to PingFed;;;
CRITICAL - P1 | Fixed | OPSfwaTechOps | SharonSmith | 6/28/2024 9:11 | 6/3/2025 14:54 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | All user are unable to sign in and access Eleven. I cna recreate on my home network on my phone. | ESC-68687 | https://jira.freewheel.tv/browse/ESC-68687 | 28/Jun/24 09:18;vmayzlin;Bridge is up. {code:java} ======= Bridge Info ======China 400 Toll: 400 919 6641 China 800 Toll: +86 10 5697 1317 United States Toll: +1 650 479 3208 United States Toll Free: 1 844 621 3956 United Kingdom Toll: +44 20 7660 8147 United Kingdom Toll Free: 0800 026 6249 France Paris Toll: +33 1 8514 8797 France Toll Free: 0805 98 12 94====== WebEx Info ======https://freewheelcc.webex.com/meet/noc1 801 089 194 {code};;;
CRITICAL - P1 | Fixed | OPSfwaTechOps | SharonSmith | 6/5/2024 9:54 | 6/12/2024 11:02 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/200460 | strata.cloud.com is down for various users. Multiple support engineers have tested and confirmed | ESC-67858 | https://jira.freewheel.tv/browse/ESC-67858 | 05/Jun/24 09:59;cphuah;Citrix has issue: Citrix DaaS is currently experiencing an issue that could impact End-Users authentication through browser. End-Users impacted are unable to login into the Workspace Experience Service.Citrix is currently experiencing an issue that could impact End-Users authentication through browser. End-Users impacted are unable to login into the Workspace Experience Service.;;;
CRITICAL - P1 | Fixed | OPSfwaTechOps | salesforce | 4/15/2024 15:26 | 4/30/2024 18:04 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Multiple agencies are reporting this issue. Media Storm (2585) Haworth Marketing Media, LLC (5433) Harmelin & Associates (844) Mediaspot (919) Evergreen Trading Company (5162) HMI (860) Canal Partners Media Inc - 1741 US International Media 2548 | ESC-66129 | https://jira.freewheel.tv/browse/ESC-66129 | 15/Apr/24 15:37;tstrege;[~aobrien] Are there any network issues that could be causing these issues?;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | tstrege | 1/4/2024 10:42 | 1/10/2024 13:42 | Internal Escalation | Strata Client |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | *{color:#ff8b00}RCA Request{color}* Issue: User Amar Pehlwan from Evergreen Trading Company is in LedgerSync and attempted to run Monthly Accruals for December 2023 from Horizon prod. This is a short list of some of the expected estimate numbers 75500, 76882, 77715, 77716, 77718, 77723, 77724, 23535. This is across various media types Radio, National Cable. This appears to be because the script requested on OPS-177459 was run on the production database and not just UAT which was Erin's intention. This is confirmed by applying a filter to the stored procedure folder searching for a name containing 'accruals'. You can see that FWS-41959 is noted in the text when you right-click on it and do a 'Script stored prod as' -> Create to -> New Query Window (this was the method Erin showed me to confirm if the script had been run in prod on SQLW6\I1). This needs to be rectified so that Evergreen data is populated (which it currently is not). PER ERIN, "[June] said she can write a script to repopulate Evergreen data so they can pull it. Can you add a request in your ticket to techops to get a copy of HMI's database restored to a network server so she can test her script before we deploy?" Can we please get a copy of their production SBMSDATA database restored somewhere product can test this script against? Primary Case ID * ** 00835235- case that prompted Jira * Jiras: OPS-181025 * Total Impacted Clients: 1 agency * Total Cases: 1 * Priority Clients Names & Case Count ** Evergreen Trading Company- 1 case * * First report: ** 1/3/2024 12:12 PM- 835235- first Agency side case submitted for issue. (Agency support hours 8am CST-7pm CST) * Resolved: * ** The Product/Dev team created a Script fix that TechOps ran tonight. Service has updated the client. * Resolution: ** TechOps is working on getting a database backup so it can be restored and a new script can be written by the Product team. ** New script has been written and tested on a Production backup. Waiting for TechOps to deploy. * Internal Stakeholders: ** Chen/Erin/JK/Tricia/Heather/Krystian CS Wiki: | ESC-62849 | https://jira.freewheel.tv/browse/ESC-62849 | 04/Jan/24 11:54;rdipallina;From: Jim Murphy the detailed updates have been tracked on https://jira.freewheel.tv/browse/OPS-181025 so far. Current status: SBMS database backup is needed for June Lu to create a script to fix the data issue and for Erin Bauer-Sauro to test that script Due to OPS-178335 , current HMI SBMS database backups are not currently available on sql-fwaOps01.gotostrata.com Keith Gugerty is pulling a current HMI SBMS database and will restore to sql-fwaOps01.gotostrata.com ;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | rchambers | 1/26/2024 11:24 | 10/21/2025 17:08 | Internal Escalation | Strata Client |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Beginning at approximately 9am Central, users started reporting latency when working in Stratasphere. We see the same internally. The same behavior appears in AEInbox as well. Steps to Reproduce: Logged into bsewell@freewheel.com admin/support account. Map to example user Chantel Paulson Go to File Cabinet Submit order search with no filters Click on first order (KSDR-FM/est. 183) and receive the error below This is not specific to any one user, one client, or specific orders and the delay has been reported when taking regular order action (such as confirming an order) or viewing an order. FYI Rachel Gotlieb, Paul Courtois Error:System.Data.SqlClient.SqlException (0x80131904): Execution Timeout Expired. The timeout period elapsed prior to completion of the operation or the server is not responding. ---> System.ComponentModel.Win32Exception (0x80004005): The wait operation timed out at System.Data.SqlClient.SqlConnection.OnError(SqlException exception, Boolean breakConnection, Action`1 wrapCloseInAction) at System.Data.SqlClient.TdsParser.ThrowExceptionAndWarning(TdsParserStateObject stateObj, Boolean callerHasConnectionLock, Boolean asyncClose) at System.Data.SqlClient.TdsParser.TryRun(RunBehavior runBehavior, SqlCommand cmdHandler, SqlDataReader dataStream, BulkCopySimpleResultSet bulkCopyHandler, TdsParserStateObject stateObj, Boolean& dataReady) at System.Data.SqlClient.SqlDataReader.TryConsumeMetaData() at System.Data.SqlClient.SqlDataReader.get_MetaData() at System.Data.SqlClient.SqlCommand.FinishExecuteReader(SqlDataReader ds, RunBehavior runBehavior, String resetOptionsString, Boolean isInternal, Boolean forDescribeParameterEncryption, Boolean shouldCacheForAlwaysEncrypted) at System.Data.SqlClient.SqlCommand.RunExecuteReaderTds(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, Boolean async, Int32 timeout, Task& task, Boolean asyncWrite, Boolean inRetry, SqlDataReader ds, Boolean describeParameterEncryptionRequest) at System.Data.SqlClient.SqlCommand.RunExecuteReader(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, String method, TaskCompletionSource`1 completion, Int32 timeout, Task& task, Boolean& usedCache, Boolean asyncWrite, Boolean inRetry) at System.Data.SqlClient.SqlCommand.RunExecuteReader(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, String method) at System.Data.SqlClient.SqlCommand.ExecuteReader(CommandBehavior behavior, String method) at System.Data.Common.DbDataAdapter.FillInternal(DataSet dataset, DataTable[] datatables, Int32 startRecord, Int32 maxRecords, String srcTable, IDbCommand command, CommandBehavior behavior) at System.Data.Common.DbDataAdapter.Fill(DataSet dataSet, Int32 startRecord, Int32 maxRecords, String srcTable, IDbCommand command, CommandBehavior behavior) at System.Data.Common.DbDataAdapter.Fill(DataSet dataSet) at ToolLib.DataAccess.SQLDataAccess.ExecuteDataSet(String ConnString, CommandType CmdType, String CmdText, SqlParameter[] CmdParams) at ToolLib.DataAccess.SQLDataAccess.SPExecuteDataSet(String StoredProcName, Object[] ParamValues) at StationAEInbox_DL.StationAEInbox_DL.GetOrderDetails(Int32 orderID, Int32 comparisonOrderID, Int32 loggedUserID, Int32 offerID) at aeinbox.orderdetails.LoadData() ClientConnectionId:d64da388-d6c1-4cfb-a888-77ba5c0ea149 Error Number:-2,State:0,Class:11 ## Trace: at System.Data.SqlClient.SqlConnection.OnError(SqlException exception, Boolean breakConnection, Action`1 wrapCloseInAction) at System.Data.SqlClient.TdsParser.ThrowExceptionAndWarning(TdsParserStateObject stateObj, Boolean callerHasConnectionLock, Boolean asyncClose) at System.Data.SqlClient.TdsParser.TryRun(RunBehavior runBehavior, SqlCommand cmdHandler, SqlDataReader dataStream, BulkCopySimpleResultSet bulkCopyHandler, TdsParserStateObject stateObj, Boolean& dataReady) at System.Data.SqlClient.SqlDataReader.TryConsumeMetaData() at System.Data.SqlClient.SqlDataReader.get_MetaData() at System.Data.SqlClient.SqlCommand.FinishExecuteReader(SqlDataReader ds, RunBehavior runBehavior, String resetOptionsString, Boolean isInternal, Boolean forDescribeParameterEncryption, Boolean shouldCacheForAlwaysEncrypted) at System.Data.SqlClient.SqlCommand.RunExecuteReaderTds(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, Boolean async, Int32 timeout, Task& task, Boolean asyncWrite, Boolean inRetry, SqlDataReader ds, Boolean describeParameterEncryptionRequest) at System.Data.SqlClient.SqlCommand.RunExecuteReader(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, String method, TaskCompletionSource`1 completion, Int32 timeout, Task& task, Boolean& usedCache, Boolean asyncWrite, Boolean inRetry) at System.Data.SqlClient.SqlCommand.RunExecuteReader(CommandBehavior cmdBehavior, RunBehavior runBehavior, Boolean returnStream, String method) at System.Data.SqlClient.SqlCommand.ExecuteReader(CommandBehavior behavior, String method) at System.Data.Common.DbDataAdapter.FillInternal(DataSet dataset, DataTable[] datatables, Int32 startRecord, Int32 maxRecords, String srcTable, IDbCommand command, CommandBehavior behavior) at System.Data.Common.DbDataAdapter.Fill(DataSet dataSet, Int32 startRecord, Int32 maxRecords, String srcTable, IDbCommand command, CommandBehavior behavior) at System.Data.Common.DbDataAdapter.Fill(DataSet dataSet) at ToolLib.DataAccess.SQLDataAccess.ExecuteDataSet(String ConnString, CommandType CmdType, String CmdText, SqlParameter[] CmdParams) at ToolLib.DataAccess.SQLDataAccess.SPExecuteDataSet(String StoredProcName, Object[] ParamValues) at StationAEInbox_DL.StationAEInbox_DL.GetOrderDetails(Int32 orderID, Int32 comparisonOrderID, Int32 loggedUserID, Int32 offerID) at aeinbox.orderdetails.LoadData() | ESC-63579 | https://jira.freewheel.tv/browse/ESC-63579 | 26/Jan/24 14:15;jmurphy;DBA [~vfava] manually rebuilt the following stored procedures: * sproc_AEI_GetOrderDetail * Sproc_AEI_GetOrderSpots * cln_GetConsolidatedInstuctionReports_v2 With those actions and will time, CPU/wait times in the DB reduced and end-user performance of the web application returned to normal.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 8/6/2024 12:19 | 8/6/2024 20:42 | External Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | AppStream: No Streaming Resources are Available - Multiple Users Strata says to contact a system administrator - no one at my company can run any of the applications. | ESC-69836 | https://jira.freewheel.tv/browse/ESC-69836 | 06/Aug/24 12:38;jmurphy;As of 11:37am CT: 47 available, 40 pending;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | rchambers | 12/30/2024 11:10 | 12/30/2024 20:36 | Internal Escalation | ALL |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Issue: Effectv reports 25+ tickets from users deactivated in OneTIM while still active in AD. Customer Impact: Users affected at 654 with a 12/29/24 end date in the system. Root Cause: TBD Next Steps: Looping in needed parties for investigation on our end. SF: 873114 ([873114¦https://stratag.lightning.force.com/lightning/r/Case/500Qj00000VVuAYIA1/view] | ESC-74533 | https://jira.freewheel.tv/browse/ESC-74533 | 30/Dec/24 13:28;MMurray;The users that were deactivated all had Effective End Date's in the Setup Users UI page set to 12/29/2024. There is a Scheduled Task job "Update User Active Flag" that runs daily at 5am and set all of the users to Active = False. Brad Biggs from Effectv had attempted to update all the effected users Effective End Date to 1/3/2025 but doing so from Mass Edit does not also update the Active flag to True and there is no Active checkbox available in the Mass Edit dialog box. Doing the same action to a single user in the Setup UI does update the Active flag to True and I think this was done for some users that had called previous to the P2 issue being created. The original decision was going to be to take the list of User Id's that Brad Biggs provided and update the setup User/AccountExecutive tables to set the Active flag to True for those users via script. However thanks to [~BFitzgerald] for saving the time and seeing the same Scheduled Task job code not only deactivates users with Effective End Dates in the past but also re-activates them if their Effective End Date is in the future and they're set to Active = False. So the job was kicked off (screenshot below) and after it ran I verified in the DB that the effected users had their Active flags set to 1 (True). The UI still wasn't showing the same so an IIS Reset was performed by Eric Nielsen of Effectv on all 10 Prod web servers and then once logged in with a fresh session the UI reflected the same changes. Brad Biggs confirmed he saw the same and will discuss with Mehran whether they move the Effective End Dates to some date far in the future or blank it out entirely but that can be done through the Setup UI. !image-2024-12-30-12-26-48-824.png¦width=1005,height=243!;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | tstrege | 10/11/2024 14:47 | 10/14/2024 18:12 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Regarding FWS-51194 the weekly sync job failed for the 2nd week in a row. Had a call with Jessie, Jignesh, Kelly, and myself troubleshooting on the server with Kelly providing log file errors that showed the jobs still failing on writing the FTP downloads to the E:\Trib and E:\Trib2 folder. There was a third folder E:\Trib3 that likely had the same error but we didn't check that specifically. The error is as follows: OnError,,,Download,\{6CFB8E14-E715-41F5-A57C-3A9B5E0D75D6},,10/6/2024 1:12:40 AM,10/6/2024 1:12:40 AM,-1073573551,0x,In Executing "C:\Program Files\PuTTY\psftp.exe" "cnt566yw@ftp.tmstv.com -pw HRB696dg -hostkey SHA256:GpFtinB/fcMY1koUh95b0DqI3zX/r9ErlEQXqWbUxUE -b C:\PackageConfigs\ImportTribune.ftp" at "E:\Trib", The process exit code was "1" while the expected was "0". OnError,,,Load Tribune Flat Files v2 2,\{2B4F43DF-4AA2-4BD2-B63A-36CDF6AF38EF},,10/6/2024 1:12:40 AM,10/6/2024 1:12:40 AM,-1073573551,0x,In Executing "C:\Program Files\PuTTY\psftp.exe" "cnt566yw@ftp.tmstv.com -pw HRB696dg -hostkey SHA256:GpFtinB/fcMY1koUh95b0DqI3zX/r9ErlEQXqWbUxUE -b C:\PackageConfigs\ImportTribune.ftp" at "E:\Trib", The process exit code was "1" while the expected was "0". Since the errors referenced C:\PackageConfigs\ImportTribune.ftp we had Kelly open that file and confirmed the contents lcd E:\Trib cd bigb get advcprogrec.txt.gz get advcskedrec.txt.gz get advcstatrec.txt.gz quit With the error referencing the "{*}at E:\Trib{*}" ** it appears there's an issue with permissions to those Trib, Trib2, Trib3 folders and the ability for whatever user runs the SSIS job to write the downloaded files there. | ESC-72021 | https://jira.freewheel.tv/browse/ESC-72021 | 11/Oct/24 14:47;MMurray;[~cphuah] [~kpham] - We are planning to do a manual run of the job that is failing but we would first like to request the Permissions on the E:\Trib, E:\Trib2, and E:\Trib3 folders to *temporarily* add "Everyone" to have Full Control access. This would only be for the duration of the manual run which is about 90 minutes. If it succeeds then we will confirm that the issue with the job is Permissions based and figure out which user (aka not Everyone) needs to be added to those folders and add that user instead for future runs. Please have this done ASAP as this issue is blocking SOS from updating program information from Trib data.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | adrake | 7/17/2024 13:18 | 7/30/2024 14:16 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Several internal and external users are reporting the error 'No streaming resources are available.' when logging in. The message comes up after clicking an icon on the dashboard after the login page. When AppStream goes to start a session, the message comes up. This has been reproduced internally with several trainer accounts and internal accounts, as well as with end user accounts. Details below. We tried logging off from the app server, clearing browsing data, restarting the browser, and recreating profiles. No effect. Incognito mode is not working either. URL: buy.gotostrata.com Internal Affected Users: vcmdtrainer@gotostrata.com, afctrainer@gotostrata.com, cjoynt@freewheel.com External Affected Users/Clients: Strategic Media Services (4726) brheault@strategicmediaservices.com Burford Advertising, Inc. (3866) jason@burfordadvertising.com cindi@burfordadvertising.com Polaris Strategies (5969) pino@polariscampaigns.com On Advertising, Inc. dwebleyfadda@onadvertising.com All affected clients so far have access to Citrix. Cheryl's system info: PC Chrome v126.0.6478.127 (Official Build) (64-bit) Our Cisco VPN Windows 10 Wireless connection Cheryl's login worked 1 week ago | ESC-69292 | https://jira.freewheel.tv/browse/ESC-69292 | 17/Jul/24 13:31;njones;https://docs.aws.amazon.com/appstream2/latest/developerguide/troubleshooting-fleets.html#troubleshooting-no-resources-available-new-streaming-session;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | adrake | 7/30/2024 12:43 | 7/30/2024 19:24 | Internal Escalation | Strata Client |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Several internal and external users are reporting the error 'No streaming resources are available.' when logging in. The message comes up after clicking an icon on the dashboard after the login page. When AppStream goes to start a session, the message comes up. This has been reproduced internally with several trainer accounts and internal accounts, as well as with several buyer accounts with different clients. | ESC-69614 | https://jira.freewheel.tv/browse/ESC-69614 | 30/Jul/24 14:28;jmurphy;AWS scaling for AppStream was updated to increase 50 servers @ 11:38a CT, updated auto-scaling factors @ 12:49p CT to a threshold of 60% and additional 7%, increased another 50 servers @ 1:05p CT to add needed capacity;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 7/12/2024 11:51 | 7/14/2024 19:54 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Users get an error message when logging in. Initially reported in this ticket:FWS-49101 Initial investigation reports this error "String or binary data would be truncated." with this stored proc SPROC_GET_STATION_ORDERS_VW | ESC-69150 | https://jira.freewheel.tv/browse/ESC-69150 | 12/Jul/24 11:54;cphuah;Link to OPS ticket - [OPS-197019] Cumulus 5728 (WW1) - SOW User getting an error message when signing in - FreeWheel JIRA;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | rchambers | 4/15/2024 15:06 | 5/1/2024 17:27 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | As of ~30 minutes ago (~1:15p CST), several users from Katz, Univision, CBS, and TTWN started reporting that they are launching apps and getting a command prompt that is asking for the user name for the app server. Screenshot attached. Users are unable to log in and launch apps. Please advise. Clients reporting the issue so far: Katz, Univision, CBS, TTWN now (701B) | ESC-66126 | https://jira.freewheel.tv/browse/ESC-66126 | 15/Apr/24 15:37;tstrege;[~aobrien] Are there any network issues that could be causing these issues?;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 4/15/2024 14:42 | 5/1/2024 17:29 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Multiple clients reporting issue Missing All Markets Database Areas for Nielsen for all years. ---------------------------- Agency missing DMA Nielsen data. Verified they have All Markets Clearance Verified in Trainer account No Data is available under Survey Selection window. Example case: User PB/Loads est 4083 for Terra Haute into VIEW Current schedule resides in SBMS Scheduling: Verified in VIEW Survey Selection does not have any data under Database Area: Nielsen2023 Urgent Estimate Not Loading on VIEW Estimate #4083 is not loading into View. Impacted clients: # Davis Elen Advertising 592 # Metro Networks Communications - Houston 701 # Mediaspot 919 # Network Affiliates/The Media Team DBA Blue Onion Media 955 # Mentzer Media 1174 # Progressive Casualty Insurance Company 1186 # Walker Advertising, Inc. 1391 # Sage Media Planning & Placement, Inc. - Washington, DC (formerly Buyline Media & Mundy Katowitz) 1415 # Dom Camera Associates (DCA) 1518 # Joseph Pedott Advertising & Marketing 1526 # National Public Media, LLC - New York (formerly Broadcasting) 1576 # Ocean Media, Inc. 1682 # Canal Partners Media Inc. (formery LUC Media) 1741 # Walz Tetrick Advertising 1763 # Zimmerman Advertising, LLC 1918 # Broadcast Buying Services (formerly Corinthian Communications, Inc.) 2228 # Intermark Group, The 2341 # Allied Advertising Limited Partnership - Boston 2358 # MediaDex, LLC 2506 # US International Media - Los Angeles 2548 # Media Storm 2585 # Mediagistic - Lutz, FL 2861 # A. Eicoff & Company 2983 # Stanley Steemer International, Inc. - Dublin 3201 # National Media, Inc. 3217 # EH+Y Media Services ( Evans Hardy & Young) 3280 # Greer, Margolis, Mitchell, Burns & Associates 3603 # Buying Time 3653 # BVK 3688 # Furniture Row, LLC 3691 # Cadent Network (formerly TelAmerica Media, LLC - Agency Side) 3711 # Crossmedia, Inc. 3828 # Target Enterprises, LLC 3867 # Barkley, Inc. 3905 # Empire Today, LLC 4055 # First Media Services (Multi Media Services Corporation) 4425 # Senders NFLMG, Inc. 4596 # Strategic Media Services 4726 # Veritone, Inc. 4736 # Gregory Welteroth Holdings, Inc. 4770 # Martin Retail Group 4844 # Continuum Media Network, Inc. 4859 # Discount Tire, America’s Tire & Discount Tire Direct (The Reinalt-Thomas Corporation) 4883 # Blue Bell Advertising Associates 4901 # Whitehardt, Inc. 4908 # MMGY Global 5010 # Cannella Response Television, LLC 5070 # True Media 5076 # Market Masters Legal 5324 # Haworth Marketing Media, LLC 5433 # Opti-Management (Vision Precision Holdings) 5524 # BBDO MW (formerly Martin Williams, Inc.) 5653 # FP1 Strategies, LLC 5655 # TCA, LLC 5686 # FreeWheel Media 5692 # Ovative 5745 # Net Conversion, LLC. 5776 | ESC-66125 | https://jira.freewheel.tv/browse/ESC-66125 | 15/Apr/24 14:54;tstrege;[~cphuah] [~kpham] Can you please take a look at this issue?;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 4/22/2024 12:53 | 6/3/2024 13:32 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Analytics was not loading for several key clients this morning. 849274 - Martin Retail (4844) 849272 - Harmelin (844) 849264 - Media Bridge (3608) 849258 - Ovative (5745) 849204 - Ocean Media (1682) | ESC-66400 | https://jira.freewheel.tv/browse/ESC-66400 | 22/Apr/24 13:12;tstrege;[~randersondukes] Client reported an Analytics outage this morning between 9:45am Central to about 10:33am. Some data seems to be loading now but Martin Retail Group is still reporting missing information from their reports. Is there a delay with Analytics currently?;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 3/11/2024 14:00 | 3/19/2024 12:29 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Escalated _________________________________ See attached error message from Anna Garza a.garza@ohpartners.com, who wrote "I've been trying to access Analytics this morning but keep getting the error below. Do you know if it's down or is this issue specific to my access?" | ESC-65028 | https://jira.freewheel.tv/browse/ESC-65028 | 11/Mar/24 16:30;crivas;NOC Updating and pending this ticket with information from FWA ENG team (in P2 Slack Channel): [~cphuah] confirmed recovery. The Engineer is looking into the DW log. [~randersondukes] I've created a ticket FWS-45433 and linked it to ESC-65028 - Will review the logs [~kgugerty] We reviewed the logs and found an out of memory error: 2024-03-11 16:04:09.744 +0000 [ERROR¦3ae03e9db96df63b¦main] :: Java::JavaLang::OutOfMemoryError : Java heap space Updating the system will require a reboot. If it is running now with out issues, we will hold on the restart until after hours. ;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 3/12/2024 18:02 | 3/15/2024 15:54 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Strata - Analytics Not Launching - Error getting Analytics read-only reports. Looker API Authentication failed Case: 844592 Agency: Universal Media User: Mark Jones Behavior/Issue/Request: Unable to launch Analytic within SBMS, multiple users | ESC-65089 | https://jira.freewheel.tv/browse/ESC-65089 | 12/Mar/24 18:16;tstrege;[~lromo] Analytics Production outage again on 3/12/2024 around 4:20pm cst. ;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 2/12/2024 9:49 | 2/26/2024 0:59 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Mike Blissett [8:32 AM] Are any servers down this morning? My team can't access sleet.stratag.com, where our ftp server sits From: DoNotReplySyncSurvey@freewheel.com Sent: Monday, February 12, 2024 8:04 AM To: [CHQ -- FWA - TAPS] ; [CHQ -- FWA - Client Service Level 3] Subject: [EXTERNAL] ERRORS found in SyncSurvey Errors found in the following Sync Survey logs. Sync Survey log files saved to \\techprod-STL\techprod-utilities\SyncSurveyLog\20240212 Minimum Free Space Violation Errors found in the following Log files: Login Error Errors found in the following Log files: Access Denied Errors found in the following Log files: Archive Errors found in the following Log files: Cannot find the file specified Errors found in the following Log files: | ESC-64114 | https://jira.freewheel.tv/browse/ESC-64114 | 12/Feb/24 09:51;cphuah;this has been fixed.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | salesforce | 2/9/2024 13:26 | 6/5/2024 19:51 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Per Chris Courtois we are waiting for responses in Eleven from orders sent at 10:48am. | ESC-64080 | https://jira.freewheel.tv/browse/ESC-64080 | 09/Feb/24 13:46;cphuah;Servers looks fine - Do we have an issue with a forwarding partner? We can add more resource for ePort tonight after hours;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | jmurphy | 2/4/2024 9:50 | 9/13/2024 11:13 | External Escalation | Dish Network |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | <Fatal> – 2024-02-02T18:45:11.315-07:00 – *InventoryRequester: System.ServiceModel.EndpointNotFoundException: There was no endpoint listening at [https://ims.gotostrata.com/ICDExportDISH/InventoryNotificationRequestService.svc] that could accept the message.* This is often caused by an incorrect address or SOAP action. See InnerException, if present, for more details. ---> System.Net.WebException: Unable to connect to the remote server ---> System.Net.Sockets.SocketException: No connection could be made because the target machine actively refused it [34.198.35.188:443¦https://urldefense.com/v3/__http:/34.198.35.188:443__;!!CQl3mcHX2A!GTH1ycxyCqwFZl63Sk64-p5Yi6sTKqInb_nkl6kYI155hSI79vi-MAYDRFv1uFHk5JcIvTopiXGI1BDQGT8WCA$] DISH ICDExportDISH inventory request calls are scheduled daily ~ 7:45PM CT. There are 2 ICDExport services: 1. Can someone please check the *ICDExportDISH* service is running in IIS. Issue first noted 2/1. Client can successfully reach the ICDExoortDISH service from the web servver browser; [https://ims.gotostrata.com/ICDExportDISH/InventoryNotificationRequestService.svc] *2. ICDExport* service is working fine. NCC is having no issues connecting with IMS PROD ICDExport service. Last worked 1/31; 7:45P CT cc: [~MPeev] [~jmurphy] [~cphuah] | ESC-63908 | https://jira.freewheel.tv/browse/ESC-63908 | 04/Feb/24 09:50;jmurphy;[~jmeckert] Is the error message provided from the DISH/Invidi application trying to connect to the IMS Inventory Request Service?;;;
DONE
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Latest Status Summary | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Comments | Fix Version
CRITICAL - P1 | Done | OPSfwaTechOps | SharonSmith | 6/17/2024 9:27 | 7/1/2024 14:02 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Eleven users are unable to log in and makegoods being sent from sell side are returning the error "Makegood rejected by system as there is error(s) about the makegood. Error: Transaction Failed: Transaction could not be processed into Eleven. Server was unable to process request. ---> Login Failed." | ESC-68252 | https://jira.freewheel.tv/browse/ESC-68252 | 17/Jun/24 09:54;rdipallina;Upgraded from P2;;;
MAJOR - P2 | Done | OPSfwaTechOps | adrake | 7/10/2024 12:46 | 8/8/2024 12:16 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Users log in to buy.gotostrata.com and get a message asking the user to Continue with Browser or Open AppStream 2.0 client, after entering creds and clicking Login. If users select Continue with Browser, they eventually get stuck at a message that says they can close the browser. There is no way for affected users to access AppStream currently. Details gathered so far: -Confirmed users accessing buy.gotostrata.com -Heather (heather.m.schmeckpeper@gmail.com) able to reproduce the issue on her Mac with Chrome (v126.0.6478.127), Safari (v17.5), and Firefox (128.0 64 bit) -Reported by 13+ clients so far: Crossroads, TCA, LLC (5686), Crossroads Media (3870), Shine United LLC (4645), Seneca Gaming (5812), TriSpark (4166), Swanson Russell (3235), Brandon Agency Inc (4050), FP1 Strategies LLC (5655), K&H, LLC (1291), AxMedia (4905), MJS Advertising (2324), Flynn Agency, LLC (formerly Martino Flynn) (3472), Access Media Services (4445) -Gathered affected user's credentials and tried to log in as the user here and could not reproduce the issue. -Logoff, recreate profile, Unlock, PW reset, Incognito/Private mode, clearing history/cache had no effect. Citrix is the only workaround. As a result of this issue, Citrix has been turned back on for all wave 1 and wave 2 clients that had it turned off. | ESC-69070 | https://jira.freewheel.tv/browse/ESC-69070 | 10/Jul/24 15:40;cphuah;AppStream is working now on the MAC machines. AWS will get the RCA soon on the Mac related release and we will keep you posted.;;;
MAJOR - P2 | Done | OPSfwaTechOps | salesforce | 4/9/2024 15:35 | 4/22/2024 14:02 | Internal Escalation | Strata Client |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Haworth Marketing Prod (5433) users could not connect to SBMS for about an hour this afternoon. Vitor noticed that the Microsoft Defender Antivirus Service was running on the SQL Server. After TechOps stopped the scan, the SQL Server had to be rebooted. Is it normal for these scans to be running during business hours? ------------ Users accessing SBMS get the message: "The database connection cannot be opened. Please contact your system administrator to verify the Database Connect Spring settings. -Verified SBMS Error in Trainer account -Escalated to CS3 for review ----------- We are not able to get into SBMS and are getting this error - attached | ESC-65951 | https://jira.freewheel.tv/browse/ESC-65951 | 09/Apr/24 16:20;jmurphy;Investigating Crowdstrike scan running using CPU% as possible cause;;;

## 2023
FIXED
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Latest Status Summary | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Comments | Fix Version
CRITICAL - P1 | Fixed | OPSfwaTechOps | hschmeckpeper | 11/30/2023 11:51 | 2/19/2024 20:12 | Internal Escalation | Strata Client |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | {color:#1d1c1d}We are getting multiples reports across multiple agencies and are able to replicate internally. Folks are not able to launch applications{color} {color:#1d1c1d}!image-2023-11-30-10-49-21-393.png!{color} | ESC-61877 | https://jira.freewheel.tv/browse/ESC-61877 | 30/Nov/23 11:56;hschmeckpeper;This is not an MRM client;;;
CRITICAL - P1 | Fixed | OPSfwaTechOps | salesforce | 12/12/2023 18:11 | 2/19/2024 20:12 | External Escalation | ALL |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | strata.cloud.com - site cannot be reached Support is able to recreate the error message in strata.cloud.com, it just spins and spins when accessing it from a browser Judy reports that she and another colleague have the same error. Judy cleared cache in Google Chrome and was not able to get in, it was discovered they were using scloud.gotostrata.com, once I directed them to the site it was working - strata.cloud.com There was a system issue with strata.cloud.com and that has been resolved by our higher-level support. | ESC-62291 | https://jira.freewheel.tv/browse/ESC-62291 | 12/Dec/23 19:18;cphuah;Worked with Citrix and it is up now.;;;
MAJOR - P2 | Fixed | OPSfwaTechOps | nramalingam | 9/28/2023 10:39 | 10/10/2023 2:34 | Internal Escalation | A&E |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only | https://freewheel.zendesk.com/agent/tickets/180283 | Hello, From today morning DAN DK finance orders are not sent to Marathon since yesterday. Received a ZD ticket from the user that campaigns are failing. Investigated it further and verified that lot of orders has been failed. Problem ticket created in ZD [https://freewheel.zendesk.com/agent/tickets/180283] Datadog link: [https://freewheel-onestrata.datadoghq.com/logs?query=service%3Afinancialbridge%20host%3Aip-10-216-7-139.eu-west-1.compute.internal-euw1-prod-app%20-status%3A%28info%20OR%20debug%29&cols=host%2Cservice&index=%2A&messageDisplay=inline&refresh_mode=paused&stream_sort=desc&viz=stream&from_ts=1695899971410&to_ts=1695900571410&live=false] In FOM: !image-2023-09-28-15-37-18-453.png! | ESC-59667 | https://jira.freewheel.tv/browse/ESC-59667 | 28/Sep/23 11:23;kpham;+[~cshah] cc: [~cphuah] ;;;
DONE
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Latest Status Summary | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Comments | Fix Version
CRITICAL - P1 | Done | OPSfwaTechOps | jweinreich | 12/15/2023 11:42 | 2/19/2024 20:11 | Internal Escalation | Altice |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/186662 | Altice can't access their Strata instances for Storm to research and build their linear schedules. Outage started on 12/13 after data center move. Client temp is FIRE as this is impacting their schedules for the holiday week. | ESC-62412 | https://jira.freewheel.tv/browse/ESC-62412 | 15/Dec/23 11:56;dvillamagna;[~jweinreich] We need the client to allow access to the below IP's and they will have access to the DB. It seems there is reluctance on their end to do this for some reason. This would correct the issue and resolve this ticket. This is the AWS SQL DB. 3.217.50.142 52.5.133.173;;;
MAJOR - P2 | Done | OPSfwaTechOps | nramalingam | 7/18/2023 7:23 | 2/19/2024 20:13 | External Escalation | Strata Client |  | T3 | Required for P1/P2 issues, full description of the current status. | MRM Only |  | DAN DK had reported an issue with some campaigns in Adazzle where the Media Plan is split when sent to Marathon. This seems to happen with the campaigns from friday Some affected campaigns are: Campaign ID Adazzle: 548524 548500 548309 548223 548488 548502 548535 Reference: https://jira.freewheel.tv/browse/OPS-165370 As per XML Loads from [~cshah] specifically for Campaign ID: 548524: It seems orders are splitting it on from Adazzle side. it does appear that the marathon adapter is creating two marathon plans instead of one. Could you please check what caused this issue? Clients are unable to book the campaign until resolution | ESC-57095 | https://jira.freewheel.tv/browse/ESC-57095 | 18/Jul/23 07:23;cwu;reviewed in defect review, Chirag is checking into it. Doesn't seem to be Financial bridge issue, Adazzle is sending media plan already split. ;;;
MAJOR - P2 | Done | OPSfwaTechOps | mplatts | 7/5/2023 11:36 | 2/19/2024 20:13 | External Escalation | Other (Specify in Comments) |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only | https://freewheel.zendesk.com/agent/tickets/173718 | [~cphuah] Environment: Adazzle-EU Affected Clients, DAN France, Havas France We have accidentally made a database change in EU production which has affected all clients, as follows. {code:java} update CommissionRelationship set enddate = '09 Dec 2020' where bepublicationid is NULL{code} We would like to revert this. [~mspencer] advised as follows: "Rolling back a committed transaction is not viable. (It's technically possible and there are some DBA tools that attempt to provide the functionality but it is very much a here-be-dragons kinda thing). My recommendation would be to do a DB restore to a support environment, bulk export the impacted table, bulk load it into a temporary table in production and then merge the dataset into the live table." Nature of customer impact: The Plan media can't be converted without the fees so they are blocked When we consult the commission, here an example : select * from commissionrelationship where agencylinkid =9430 | ESC-56678 | https://jira.freewheel.tv/browse/ESC-56678 | 05/Jul/23 12:34;cphuah;Stan, [~mcecilesanto] will attach the restore script soon. cc [~sdaskalov] [~mplatts] ;;;
NORMAL - P3 | Done | OPSfwaTechOps | khines | 2/12/2023 17:13 | 4/24/2024 11:25 | External Escalation | Turner Broadcasting |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only | https://freewheel.zendesk.com/agent/#/tickets/164814 | Network ID: 48804 Summary of the issue report (symptom): from client - needs work ASAP - " TBS streams - schedules appear to be missing in LRM. " They want stuff re-pushed, but we need this done ASAP. Please help me assign this to the correct group if this is wrong. | ESC-52334 | https://jira.freewheel.tv/browse/ESC-52334 | 12/Feb/23 17:26;rzheng;Hi [~khines] , Could you elaborate a little bit more what's LRM is? And what schedules needs to be re-pushed? Any UI links or other references?;;;
UNRESOLVED
Priority | Resolution | Assignee | Reporter | Created | Updated | Escalation Type | Client(s) | FreeWheel Platform | Ticket Holder | Latest Status Summary | Client Support Type | Zendesk Client | Description | Ticket Number | Issue Link | Comments | Fix Version
MAJOR - P2 |  | OPSfwaTechOps | rquam | 3/22/2023 9:40 | 4/5/2023 22:58 | Internal Escalation | ALL |  |  | Required for P1/P2 issues, full description of the current status. | MRM Only |  | Multiple agencies are unable to load Analytics in SBMS due to the error "Error Loading Analytics Page. Error Code: Connection Refused" (screenshot attached.) We are able to replicate this in the following trainer accounts: Media Bridge (3608) Asher (5879) Crossmedia (3828) | ESC-53513 | https://jira.freewheel.tv/browse/ESC-53513 | 22/Mar/23 09:47;lromo;It looks like Prod is down. !image-2023-03-22-08-46-52-087.png¦width=517,height=394!;;;